## Summary
Phase | Tasks | Hours | Days | Weeks | Key Deliverable
Phase 0 — Scaffolding | 16 | 0 | 0 | 1–1.5 | Project builds, parser tested, CI green
Phase 1 — tvOS MVP | 29 | 0 | 0 | 5–6 | Fully functional tvOS app on TestFlight
TOTAL | 45 | 0 | 0 | 6–7.5

## Phase 0 — Scaffolding
ID | Task | Subtasks / Acceptance Criteria | Owner | Est (hrs) | Priority | Depends On | Status | Notes
🔧 PROJECT SETUP
P0-01 | Create Xcode project (tvOS target) | • tvOS app target with SwiftUI lifecycle • Bundle ID, team signing, deployment target (tvOS 17.0+) • Git repo init with .gitignore (Xcode, SPM) | Lead | 2 | P0 | — | To Do | Use Xcode 16+ for latest SwiftUI
P0-02 | Add empty KMP shared module | • Kotlin Multiplatform module with iOS framework target • Gradle build compiles successfully • SwiftUI app can import shared framework (empty) • Directory structure: shared/src/commonMain, iosMain | Lead | 4 | P0 | P0-01 | To Do | Use KMP wizard or SKIE for Swift interop
P0-03 | Configure SPM dependencies | • VLCKit (via SPM or CocoaPods) • Kingfisher → replaced by Coil (add later via KMP) • SQLDelight Gradle plugin in shared module • Ktor client in shared module | Lead | 3 | P0 | P0-02 | To Do | Pin exact versions in Package.resolved
P0-04 | Project directory structure | • /App (SwiftUI entry, tvOS views) • /Shared (KMP module) • /Features (per-feature modules) • /Resources (assets, strings) • README with build instructions | Lead | 1 | P0 | P0-01 | To Do
🧪 M3U PARSER + TESTS
P0-05 | Implement M3U/M3U8 parser (KMP) | • Parse #EXTINF lines (name, group-title, tvg-id, tvg-logo, tvg-name) • Parse stream URLs (http/https) • Handle UTF-8 BOM, Windows line endings (\r\n) • Handle missing/malformed fields gracefully (skip, don't crash) • Return List<Channel> with error count | Dev | 6 | P0 | P0-02 | To Do | Write in commonMain so it runs on all targets
P0-06 | Collect 10+ malformed M3U samples | • At least 10 real-world playlists covering: - UTF-8 BOM + Windows CRLF - Missing group-title - Non-standard #EXTINF tags - Empty lines / comments mid-file - Huge file (5000+ entries) - Totally broken (HTML error page) • Store in shared/src/commonTest/resources/ | Dev | 2 | P0 | — | To Do | Anonymize any real provider URLs
P0-07 | Unit tests for M3U parser | • ≥95% line coverage on parser module • Test each malformed sample parses without crash • Test correct field extraction (name, group, logo, tvg_id) • Test error counting (X entries skipped) • Test empty input, null URL, huge file (>5K entries) • All tests pass on JVM + iOS targets | Dev | 4 | P0 | P0-05, P0-06 | To Do | Use kotlin.test for KMP-compatible tests
P0-08 | Implement Xtream Codes API client (KMP) | • Authenticate: GET /player_api.php?username=X&password=Y • Get live categories, live streams, VOD categories, VOD streams, series • Parse JSON responses to shared models • Handle auth failure, timeout, malformed JSON gracefully • Ktor HttpClient with configurable timeout | Dev | 6 | P0 | P0-03 | To Do | Use Ktor + kotlinx.serialization
P0-09 | Unit tests for Xtream client | • Mock HTTP responses for all endpoints • Test auth success + failure • Test malformed JSON handling • Test timeout behavior • ≥90% coverage | Dev | 3 | P0 | P0-08 | To Do | Use Ktor MockEngine
⚙️ CI / CD PIPELINE
P0-10 | GitHub Actions: build tvOS | • Workflow triggers on push to main + PR • Build tvOS target (xcodebuild) • Cache SPM + Gradle dependencies • Fail on compiler warnings (-Werror) • Build time target: <5 min | Lead | 3 | P0 | P0-01 | To Do | Use macos-14 runner for Xcode 16
P0-11 | GitHub Actions: run KMP tests | • Run shared module tests (JVM + iOS simulator) • Report test results as PR check • Fail PR if any test fails • Upload test report artifact | Lead | 2 | P0 | P0-07 | To Do | JVM tests are faster — run first
P0-12 | GitHub Actions: lint + format | • SwiftLint for Swift code • ktlint for Kotlin code • Auto-format on PR (or fail) • Consistent code style from day 1 | Lead | 2 | P0 | P0-10 | To Do | Add .swiftlint.yml + .editorconfig
P0-13 | TestFlight setup | • App Store Connect: create app record • Provisioning profiles (dev + distribution) • Manual TestFlight upload from local (automate later) • Internal testing group created | Lead | 2 | P0 | P0-01 | To Do | Need Apple Developer account ($99/yr)
📐 ARCHITECTURE FOUNDATION
P0-14 | SQLDelight schema v1 | • Create all tables from spec (Playlist, Channel, VodItem, WatchProgress, EpgProgram, SchemaVersion) • PRAGMA foreign_keys = ON • All indexes from spec • Verify compiles on commonMain • Write 3 basic queries (insert playlist, get channels, upsert progress) | Dev | 3 | P0 | P0-03 | To Do | Schema from design spec §06
P0-15 | TCA skeleton (tvOS) | • Install TCA via SPM • Create AppReducer with stub features • Navigation router with sidebar destinations (Home, LiveTV, Movies, Shows, Emby, Favorites, Settings) • Compiles and shows empty sidebar on tvOS simulator | Lead | 4 | P0 | P0-03 | To Do | TCA 1.x with @Reducer macro
P0-16 | Koin DI setup (KMP) | • Koin module with stubs for repositories • PlaylistRepository, ChannelRepository, EpgRepository protocols • Wire into Swift via helper functions • Verify DI resolves correctly in unit test | Dev | 2 | P0 | P0-02 | To Do
|  |  | TOTAL | 49 |  |  |  | ≈ 6 working days (1 dev) or 3 days (2 devs)

## Phase 1 — tvOS MVP
ID | Task | Subtasks / Acceptance Criteria | Owner | Est (hrs) | Priority | Depends On | Status | Notes
▶️ VIDEO PLAYER
P1-01 | AVPlayer wrapper (SwiftUI) | • AVPlayer wrapped in UIViewControllerRepresentable for tvOS • Play/pause/seek controls • Handle HLS (.m3u8) and MP4 streams • Report player state (loading, playing, paused, error) • Subtitle track selection (embedded + external SRT) | Dev | 8 | MVP | P0-15 | To Do | Use AVPlayerViewController for native tvOS controls
P1-02 | VLCKit fallback player | • VLCMediaPlayer wrapper matching same interface as AVPlayer wrapper • Handle MPEG-TS, MKV, exotic codecs • Same state reporting (loading, playing, paused, error) • On-demand resource download (don't bloat binary) | Dev | 6 | MVP | P1-01 | To Do | Load via ODR to keep base binary small
P1-03 | FFprobeKit stream probing | • Probe stream URL before player selection (<200ms target) • Detect container format + codec • Route to AVPlayer (HLS, MP4/H.264) or VLCKit (everything else) • Timeout after 500ms → default to AVPlayer • Log probe results for analytics | Dev | 4 | MVP | P1-01 | To Do | FFprobeKit is lightweight, no full FFmpeg
P1-04 | Reconnect logic (exponential backoff) | • Detect playback failure (timeout, 403, stream ended) • Auto-retry up to 3 times with backoff (1s, 3s, 7s) • Re-probe stream on each retry • After 3 failures: show error state with manual retry + "Try VLCKit" • Log error codes for analytics | Dev | 4 | MVP | P1-01, P1-03 | To Do
P1-05 | Player state machine (KMP shared) | • Shared PlayerState enum (idle, loading, probing, playing, paused, error, reconnecting) • State transitions enforced (no invalid jumps) • Expose via Kotlinx.coroutines StateFlow • Swift consumes via TCA integration | Dev | 3 | MVP | P0-02 | To Do | Core of the shared player logic
📡 LIVE TV
P1-06 | Channel list screen (tvOS) | • Sidebar category filter (groups from M3U) • Channel grid/list with logo, name, now/next EPG • Focus engine: smooth scrolling, scale on focus • Tap → full-screen player • Channel number badge on each tile | Dev | 8 | MVP | P0-15, P0-05 | To Do | LazyVGrid with focusable items
P1-07 | Channel number entry overlay | • Number input via Siri Remote (game controller API or numpad) • Overlay shows typed digits with 2s auto-dismiss • Jump to matching channel_num • If no match, show brief "Not found" toast | Dev | 3 | MVP | P1-06 | To Do | Use GCController API for number buttons
P1-08 | Quick Channel Switcher overlay | • Swipe down during playback → overlay with favorites + recents • Horizontal scrollable row with channel tiles • Select → instant channel switch (no return to list) • Swipe up or timeout → dismiss overlay • Audio continues during overlay | Dev | 4 | MVP | P1-01, P1-06 | To Do | Critical UX — every IPTV app needs this
P1-09 | Full-screen player overlay (tvOS) | • Tap to show/hide transport controls • Channel name + now playing (from EPG) • Progress bar for VOD, live indicator for streams • Subtitle / audio track picker • Swipe down → quick channel switcher • Auto-hide after 5s inactivity | Dev | 6 | MVP | P1-01, P1-08 | To Do
P1-10 | Player error / buffering state | • Full-screen "No Signal" with spinner • Auto-retry countdown (visible to user) • Manual "Retry" button • "Try alternate player" button (AVPlayer ↔ VLCKit) • Error code display for troubleshooting | Dev | 3 | MVP | P1-04 | To Do
📺 EPG
P1-11 | XMLTV parser (incremental, KMP) | • SAX-style streaming parser (not DOM) • Parse <programme> elements incrementally • INSERT OR REPLACE into SQLite (upsert) • Background thread with progress callback • Handle 50–200 MB files without OOM • Purge programs older than 7 days | Dev | 8 | MVP | P0-14 | To Do | Memory budget: <100MB during parse
P1-12 | EPG list view (now/next badges) | • On channel list: show current + next program • Program name + time range • Progress bar showing how far into current program • Refresh every 60s • Tap on EPG badge → program detail sheet | Dev | 4 | MVP | P1-11, P1-06 | To Do
P1-13 | EPG grid view (timeline) | • Horizontal scrollable timeline (24h range) • Vertical channel list (left axis) • Program blocks with title + duration • "Now" marker line • Focus on program → show detail • Select program → play channel • Voice search button (prominent) | Dev | 10 | MVP | P1-11 | To Do | Most complex UI component in the app
🏠 HOME + NAVIGATION
P1-14 | tvOS sidebar navigation | • Persistent sidebar: Home, Live TV, Movies, TV Shows, Emby, Favorites, Settings • Focus-driven with scale + highlight on focused item • Sidebar collapses when content is focused • Deep link support for Top Shelf | Dev | 4 | MVP | P0-15 | To Do | TabView with .sidebarAdaptable on tvOS 18+
P1-15 | Home screen | • Hero card with continue watching (parallax on focus) • Favorites row (horizontal scroll) • Recent channels row • Recently watched VOD row • Empty states for first-run | Dev | 6 | MVP | P1-14 | To Do
P1-16 | Now Playing mini-bar | • Persistent bar at bottom of Home when stream is active • Shows: live dot, channel name, program title • Tap → return to full-screen player • Animates in/out smoothly • Respects safe areas | Dev | 3 | MVP | P1-01, P1-15 | To Do | Similar to Apple TV Music mini-player
P1-17 | Favorites & recents engine (KMP) | • Toggle favorite on Channel (update is_favorite) • Track watch progress in WatchProgress table • Query: get favorites ordered by name • Query: get recents ordered by updated_at DESC • Expose via repository with StateFlow | Dev | 3 | MVP | P0-14 | To Do
🎬 EMBY INTEGRATION
P1-18 | Emby API client (KMP) | • Authenticate: POST /Users/AuthenticateByName • Get libraries: GET /Library/MediaFolders • Get items: GET /Items (movies, series, episodes) • Get stream URL: GET /Items/{id}/PlaybackInfo • Report playback progress: POST /Sessions/Playing • Handle auth token refresh + expiry | Dev | 8 | MVP | P0-03 | To Do | Ktor client with auth interceptor
P1-19 | Emby browser screen (tvOS) | • Library selector (Movies, TV Shows, Music, etc.) • Poster grid with title + year • Focus parallax on posters • Continue watching row (from Emby API) • Pull-to-refresh | Dev | 6 | MVP | P1-18, P1-14 | To Do
P1-20 | Detail view (movie/show) | • Hero backdrop image • Title, year, rating, genre, description • Play / Resume button • For series: season picker → episode list with thumbnails • Related content row (if available) | Dev | 5 | MVP | P1-19 | To Do | Reuse for both IPTV VOD and Emby
⚙️ SETTINGS + ONBOARDING
P1-21 | Onboarding flow (tvOS) | • Welcome screen with app branding • Legal disclaimer (full text from spec) • Add first source: M3U URL / Xtream / Emby • QR code for iOS pairing (placeholder for v2) • Test connection → parse → Home | Dev | 5 | MVP | P0-15 | To Do | Legal text is critical for App Store approval
P1-22 | Add Source screen | • Source type tabs (M3U, Xtream, Emby) • M3U: URL field + optional EPG URL • Xtream: Server URL, username, password • Emby: Server URL, username, password • "Test Connection" button with spinner • Save to Playlist table + Keychain | Dev | 5 | MVP | P0-14, P1-18 | To Do | Credentials → Keychain, never SQLite
P1-23 | Settings screen | • Source management (edit, delete, reorder) • Playback preferences (default player, buffer size) • Section visibility (hide/show Live TV, Movies, etc.) • Default launch section • About / version / legal | Dev | 4 | MVP | P1-14 | To Do
P1-24 | Top Shelf extension | • TV Top Shelf Content Provider • Sectioned layout: Favorites + Recents • Poster images from channel logos / VOD posters • Deep link to channel / content on tap • Refresh on app background | Dev | 4 | MVP | P1-17 | To Do | Requires separate extension target
🔗 INTEGRATION + POLISH
P1-25 | Playlist auto-refresh | • Refresh on app launch (if stale per refresh_hrs) • Background refresh via BGTaskScheduler • User-configurable interval (1/2/3/7 days) • Show last-synced timestamp in Settings • Don't refresh if on cellular (iOS) | Dev | 3 | MVP | P0-05, P0-08 | To Do
P1-26 | Movies screen (VOD from IPTV) | • Extract VOD movies from M3U/Xtream • Poster grid with genre filter + sort (A-Z, year, recent) • Search within movies • Detail view → play • Handle missing posters gracefully | Dev | 5 | MVP | P0-05, P1-14 | To Do | Reuse detail view from P1-20
P1-27 | TV Shows screen (VOD series) | • Series grid → Season list → Episode list • Episode thumbnails (if available) • Resume from last-watched episode • Mark as watched | Dev | 5 | MVP | P0-05, P1-14 | To Do
P1-28 | AirPlay 2 sender | • Expose AVRoutePickerView in player overlay • AirPlay icon in transport controls • Works automatically with AVPlayer • VLCKit: requires manual AirPlay setup | Dev | 2 | MVP | P1-01 | To Do | Free with AVPlayer — just expose the UI
P1-29 | Performance pass (NFR targets) | • Profile with Instruments on Apple TV HD • Cold start <2.2s • Channel switch <1.5s • 60fps scrolling on 4K, 30fps min on HD • Memory <450MB peak during EPG + playback • Fix any violations before TestFlight | Lead | 6 | MVP | All P1 | To Do | Blocks TestFlight upload
|  |  | TOTAL | 145 |  |  |  | ≈ 5–6 weeks (1 dev) or 3 weeks (2 devs with pairing)